## Matrix
Spring 2018 Bulletin Process Map Matrix
Instruction & Student Services | [6 empty] | 2017-10-20 |  | 2017-10-25 |  |  |  | 2017-12-06
[7 empty] | AA posts PDF to web 1st link is Front Cover 2nd link is schedule |  | Copies of Bulletin ready for distribution. | REPRINT |  |  | AA posts PDF to web 1st link is Front Cover 2nd link is schedule
10
Registrar |  | 2017-10-02 |  |  | 2017-10-18 | [5 empty] | 2017-12-04
|  | Completes scheduling |  |  | Done making edits. Submit to IR by 5pm | [5 empty] | Done making edits. Submit to IR by 5pm
|  | 3 |  |  | 6 | [5 empty] | 2
Institutional Research | 2017-09-20 |  | 2017-10-05 |  | 2017-10-18 | 2017-10-20 |  |  |  |  | 2017-12-04 | 2017-12-06
| Submits semester dates to Ray |  | Proof is distributed to Bulletin Group by 8am |  | Done making edits by 5pm | Saves final PDF in T:\Bulletin by 5pm |  |  |  |  | Done making edits by 5pm | Saves final PDF in T:\Bulletin by 5pm
| 1 |  | 4 |  | 7 | 9 |  |  |  |  | 3 | 5
Print Shop |  |  |  |  | 2017-10-18 |  |  | 2017-10-23 |  |  | 2017-12-04
[5 empty] | Done making edits by 5pm |  |  | Gets final draft from T:\Bulletin, prints 1000 copies at 8am |  |  | Done making edits by 5pm
[5 empty] | 8 |  |  | 11 |  |  | 4
Bulletin Group | 2017-09-20 |  |  | 2017-10-11 | [5 empty] | 2017-11-29
| Course scheduling changes due by 5pm |  |  | Submit updates to: Registrar=schedule, IR=Front, Print Shop=WTCE by 5pm | [5 empty] | Submit updates to: Registrar=schedule, IR=Front, Print Shop=WTCE by 5pm
| 2 |  |  | 5 |  |  |  |  | 12 | 1 |  |  | 6